Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 30 March 2026 |
| --- | --- |
| Project Name | Video Conferencing App |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

| Sprint | User Story ID | Feature | User Story Description | Story Points |
| --- | --- | --- | --- | --- |
| Sprint 1 | USN-1 | User Registration | User can register using name, email, and password | 2 |
| Sprint 1 | USN-2 | Data Security | Password is securely stored as a bcrypt hash in MongoDB | 2 |
| Sprint 1 | USN-3 | User Login | Registered user can log in using email and password | 2 |
| Sprint 1 | USN-4 | JWT Generation | User receives a signed JWT token after successful login | 2 |
| Sprint 2 | USN-5 | Protected Routes | Unauthorized users cannot access protected routes without valid JWT | 3 |
| Sprint 2 | USN-6 | Home Dashboard | Authenticated user sees name and options (Create/Join Meeting) | 1 |
| Sprint 2 | USN-7 | Create Meeting | User can create a meeting using a custom room name | 2 |
| Sprint 2 | USN-8 | Join Meeting | User can join a meeting using a room code | 2 |
| Sprint 3 | USN-9 | Media Tracks | Camera and microphone are automatically created and published on joining | 3 |
| Sprint 3 | USN-10 | Audio Control | User can mute/unmute microphone during session | 2 |
| Sprint 3 | USN-11 | Video Control | User can start/stop camera without leaving the meeting | 2 |
| Sprint 3 | USN-12 | Participant Video Grid | Remote users are auto-discovered and displayed in responsive grid | 3 |
| Sprint 4 | USN-13 | Leave Meeting | User can leave meeting and release media tracks | 2 |
| Sprint 4 | USN-14 | Logout | User can logout, clearing JWT and redirecting to login page | 1 |
| Sprint 4 | USN-15 | Responsive UI | Application adapts to different screen sizes using Tailwind CSS | 2 |

Estimation Logic Summary Table:

| Effort Level | Story Points | Description | Examples |
| --- | --- | --- | --- |
| High Effort | 3 Points | Complex logic, integrations, or real-time features | Protected routes, media publishing, participant grid |
| Standard Effort | 2 Points | Core functional features | Login, registration, meeting creation/join, media controls |
| Low Effort | 1 Point | Simple UI or state management tasks | Dashboard UI, logout |